## PSU FY18-23 Capital Plan
Plymouth State University
6 Year Capital Plan
All Values in Millions of Dollars
April 2018
|  |  |  | FY18-FY23 | FY 18 | FY 19 | FY20 | FY 21 | FY 22 |  | FUNDING SOURCE
| Funded Capital Projects | Anticipated Completion | Total Project Budget | Projected Costs | [5 empty] | FY23 | Gifts | IFB | Reserves/ Operations | HEFA Bonds | State | Grants | Strategic Funding | TBD
Major Capital Projects
| Hyde Hall Projects ($2M from Gifts, $4.5M State) | Ongoing | 17 | 15.68 | 1.18 | 2 | 3 | 3.5 | 4 | 2 | 2 |  | 9.2 |  | 4.5
| Hyde Electrical Upgrade | Ongoing |  | 0.13 | 0.13 | 0 | 0 | 0 | 0 | 0
| Hyde Fire Alarm System Replacement | Ongoing |  | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0
| Hyde Building Upgrade w/design: Ceiling & Light Upgrade | Ongoing |  | 1.5 | 0.75 | 0.75 | 0 | 0 | 0 | 0
| Future Hyde Hall Projects | Ongoing |  | 13.75 | 0 | 1.25 | 3 | 3.5 | 4 | 2
| PE Ctr Reno Projects ($2M Gifts) | Ongoing | 4.4 | 4.4 | 0.4 | 0 | 1 | 1.5 | 1.5 | 0 | 2 |  | 2.4
| PE Center Roof Replacement | 2018-09-01 | 0.6 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0
| Future PE Center Projects | Ongoing |  | 4 | 0 | 0 | 1 | 1.5 | 1.5 | 0
| Auxiliary Projects | Ongoing | 15.8 | 15.8 | 1.6 | 7.6 | 2.6 | 1 | 2 | 1 |  |  | 15.8
| Belknap Renovation | 2020-09-01 | 2.6 | 2.6 | 0 | 0.3 | 2.3 | 0 | 0 | 0 |  |  | 2.6
| Smith Renovation | 2018-09-01 | 8.9 | 8.9 | 1.6 | 7.3 | 0 | 0 | 0 | 0 |  |  | 8.9
| Other Auxiliary Projects | Ongoing | 3.3 | 4.3 | 0 | 0 | 0.3 | 1 | 2 | 1 |  |  | 4.3
| Cluster & Open Labs/ Restructuring |  |  | 15 | 7.1 | 7.9 | 0 | 0 | 0 | 0 |  |  | 7 |  | 3 |  | 5
| D&M FAB Lab (1st Floor) | 2018-09-01 | 0.6 | 0.6 | 0.1 | 0.5 | [6 empty] | 0.1
| D&M Creater Space (4th Floor) | 2019-09-19 | 1.9 | 1.9 | 0.2 | 1.7 | [6 empty] | 0.5 |  |  |  | 1.4
| PE Center HHP Renovation ($3M STATE FUNDING) | 2018-09-01 | 10 | 10 | 4.3 | 5.7 | [6 empty] | 4.7 |  | 3 |  | 1.8
| Hyde 120/220 | 2017-09-01 | 1.9 | 0.7 | 0.7 | [11 empty] | 0.7
| Student Svc Ctr - Speare (includes HVAC) | 2018-09-01 | 2.3 | 1.8 | 1.8 | [7 empty] | 1.2 |  |  |  | 1.1
| Other Major Projects: |  |  | 10.4 | 6.1 | 3.6 | 0.7 | 0 | 0 | 0 | 2 |  | 2.8 | 5.6
| PSU Entrance Gateway - High Street | 2018-09-01 | 0 | 0
| Turf Field with Lights ($2M Gifts) | 2019-08-01 | 4.4 | 4.4 | 0.1 | 3.6 | 0.7 |  |  |  | 2 |  | 2.4
| Merrill Place ($33m total) | 2017-09-01 | 33 | 5.6 | 5.6 | [8 empty] | 5.6
| Episcopal Church | Ongoing | 0.4 | 0.4 | 0.4 | [7 empty] | 0.4
| Subtotal Major Capital Projects |  | 91.7 | 61.28 | 16.38 | 21.1 | 7.3 | 6 | 7.5 | 3 | 6 |  | 37.2 | 5.6 | 7.5 |  | 5
Program Funds (Annual Recurring)
| E&G - Deferred Maintenance Projects (6XB291) | Ongoing | 11.7 | 12.33 | 0.63 | 4.8 | 3 | 1.5 | 1.2 | 1.2 |  |  | 12.33
| Cogen Roof |  |  | 0 | 0
| Memorial 3rd Floor Renovation |  |  | 0
| Rounds Heating System |  |  | 0.2 |  |  | 0.2
| Speare Chiller Replacement |  |  | 0.5 | 0.1 | 0.4
| Speare Roof Replacement |  |  | 0.495 | 0.125 | 0.37
| Speare Window Replacement |  |  | 0.3 |  |  | 0.3
| Student Apts - Infrastructure (Steamline) & Renovations |  |  | 2.4 | 0.4 | 2
| CoGen plant |  |  | 0.25 |  | 0.25
| Highland Hall Windows |  |  | 0.25 |  |  | 0.25
| Classroom Modernization | Ongoing | 1.5 | 2 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 2
| Subtotal Program Funds (Recurring) |  |  | 14.33 | 0.63 | 4.8 | 3.5 | 2 | 1.7 | 1.7 |  |  | 14.33
Total Capital Projects |  |  |  | 75.61 | 17.01 | 25.9 | 10.8 | 8 | 9.2 | 4.7 | 6 |  | 51.53 | 5.6 | 7.5 |  | 5
Note on I52: Laurie Wilcox: $300k for production studio in Highland